## 3-WEEK LOOK-AHEAD
▲ TRIANGLE PROJECT MANAGEMENT ¦ THREE-WEEK LOOK-AHEAD SCHEDULE | [15 empty] | SITE MGMT
Lean Construction · Last Planner System® Principles · Short-Interval Site Planning
PROJECT: |  | [Project Name] |  |  | WEEK COMMENCING: |  |  |  | [Date] |  |  |  | REPORT BY: |  |  | [Project Planner / Site Manager]
# | WBS | Activity / Task Description | Trade / Sub | Owner | WEEK 1 ([Date] – [Date]) |  |  |  |  | WEEK 2 ([Date] – [Date]) |  |  |  |  | WEEK 3 ([Date] – [Date]) |  |  |  |  | Constraints / Lookahead Notes | % Plan Complete
# | WBS | Description | Trade | Owner | Mon [D1] | Tue [D2] | Wed [D3] | Thu [D4] | Fri [D5] | Mon [D6] | Tue [D7] | Wed [D8] | Thu [D9] | Fri [D10] | Mon [D11] | Tue [D12] | Wed [D13] | Thu [D14] | Fri [D15] | Constraints / Notes | % PPC
CIVIL & STRUCTURAL
1 | 1.1 | [Activity — e.g. Core Wall Formwork Level X] | [Subcontractor] | [Site Foreman] | ■ | ■ | ■ | ■ | ■ | [10 empty] | [Constraint or note] | [%]
2 | 1.2 | [Activity — e.g. Core Wall Reinforcement] | [Subcontractor] | [Site Engineer] |  |  |  | ■ | ■ | ■ | ■ | [8 empty] | [Constraint or note] | [%]
3 | 1.3 | [Activity — e.g. Concrete Pour] | [Subcontractor] | [PM / Engineer] |  |  |  |  | ■ | [10 empty] | [Constraint or note] | [%]
4 | 1.4 | [Activity — e.g. Suspended Slab Formwork] | [Subcontractor] | [Site Foreman] | [5 empty] | ■ | ■ | ■ | ■ | ■ | [5 empty] | [Constraint or note] | [%]
MEP WORKS
5 | 2.1 | [Activity — e.g. Electrical First Fix] | [Subcontractor] | [MEP Coordinator] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | [5 empty] | [Constraint or note] | [%]
6 | 2.2 | [Activity — e.g. Mechanical Pipe Insulation] | [Subcontractor] | [MEP Engineer] | ■ | ■ | ■ | [12 empty] | [Constraint or note] | [%]
7 | 2.3 | [Activity — e.g. HVAC Duct Installation] | [Subcontractor] | [MEP Coordinator] | [7 empty] | ■ | ■ | ■ | ■ | ■ | ■ |  |  | [Constraint or note] | [%]
ARCHITECTURAL / FINISHES
8 | 3.1 | [Activity — e.g. Raised Access Floor Installation] | [Subcontractor] | [Site Manager] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | [8 empty] | [Constraint or note] | [%]
9 | 3.2 | [Activity — e.g. Internal Blockwork] | [Subcontractor] | [Site Foreman] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | [7 empty] | [Constraint or note] | [%]
10 | 3.3 | [Activity — e.g. Curtain Wall Mock-Up Inspection] | [Subcontractor + Client] | [PM / Engineer] |  |  |  | ■ | [11 empty] | [Constraint or note] | [%]
EHS & SITE MANAGEMENT
11 | 4.1 | Weekly Site Safety Inspection — All Areas | [EHS Officer] | [EHS Manager] | ■ |  |  |  | ■ | ■ |  |  |  | ■ | ■ |  |  |  | ■ | Toolbox Talks conducted each Monday (all trades) | [%]
12 | 4.2 | [Activity — e.g. Structural Inspection (Pre-Pour)] | [Struct. Engineer] | [PM] | [5 empty] | ■ | [9 empty] | ITP hold point — sign-off before pour approval | [%]
13 | 4.3 | [Activity — e.g. Crane Maintenance] | [Crane Maintenance] | [Site Manager] |  |  | ■ | [12 empty] | [Constraint or note] | [%]
PERCENT PLAN COMPLETE (PPC) — Lean Construction KPI ¦ Target: ≥ 80% | [20 empty] | [%]
LEGEND:
■ | Planned Work |  | ● | Completed Work |  |  | Not Scheduled |  | [Amber] | Constraint Identified
▲ Triangle PM · © 2026 · Last Planner System® is a registered trademark of the Lean Construction Institute