## RISK REGISTER
▲ TRIANGLE PM ¦ RISK REGISTER | [12 empty] | RISK MANAGEMENT
ISO 31000 : 2018 · PMBOK 7th Ed. · Probability × Impact · Pre & Post-Mitigation Scoring · Owner & Action Tracking
PROJECT: |  | [Project Name] |  |  |  |  | PROJECT NO: |  |  |  | [Project No.] |  |  | CONTRACT TYPE: |  |  |  | [FIDIC / NZS / Other]
CLIENT: |  | [Client Name] |  |  |  |  | PREPARED BY: |  |  |  | [Name / Role] |  |  | REPORT DATE: |  |  |  | [DD-Mon-YYYY]
Risk ID | Category | Risk Description (What Could Go Wrong) | Cause (Why It Might Happen) | Consequence (Effect If It Occurs) | WBS Ref. | Risk Owner | Prob. (1–5) | Impact (1–5) | Score (P×I) | Rating | Response Strategy | Mitigation / Control Actions | Action Owner | Action Due Date | Res. Prob. | Res. Impact | Res. Score | Residual Rating | Status | Last Reviewed | Notes / Remarks
R001 | Schedule | Piling programme delay due to ground conditions differing from site investigation report | Insufficient ground investigation data; unforeseen obstructions or soil conditions | Critical path delay 4–8 weeks; additional cost for modified piling method; potential EOT claim | 2.1.2 | [PM / Planner] | 3 | 5 | 15 | VERY HIGH | Mitigate | Commission supplementary SI boreholes at 20m grid. Establish contingency piling method with sub-contractor. Include force majeure clause in piling contract. | [Site Manager] | [Date] | 2 | 3 | 6 | MEDIUM | Open - Active | [Date] | FIDIC Sub-Clause 4.12 applies
R002 | Design | IFC drawing release delayed — structural drawings not issued to programme | Under-resourced design team; design coordination delays; scope change mid-design | Construction programme delay; abortive work on site; subcontractor idle time claims | 1.2.2 | [Lead Engineer] | 3 | 4 | 12 | HIGH | Mitigate | Agree weekly drawing release schedule with design lead. Tracking in IFC register. Escalation protocol if release falls >1 week behind. | [PM] | [Date] | 2 | 3 | 6 | MEDIUM | Open - Active | [Date] | Required Information Dates linked to programme
R003 | Procurement | Long-lead equipment (façade / lifts / MEP plant) delivery delay | Supply chain disruption; manufacturing delays; port congestion; force majeure | Programme delay 6–12 weeks; extended preliminaries; knock-on to fit-out sequence | 1.3.2 | [Procurement] | 3 | 5 | 15 | VERY HIGH | Mitigate | Lock orders at contract award. Track factory production weekly. Identify alternative suppliers. Maintain 6-week buffer in programme. | [Contracts Mgr] | [Date] | 2 | 4 | 8 | MEDIUM | Open - Active | [Date] | Lifts and façade identified as critical long-lead items
R004 | Cost | Material price escalation (steel, concrete, copper) above tender allowance | Inflationary pressure; commodity market volatility; currency fluctuation | Cost overrun 3–8% on material-heavy packages; margin erosion; budget breach | 2.0 | [QS / Controls] | 3 | 4 | 12 | HIGH | Transfer | Include price escalation clauses in subcontracts. Obtain fixed-price quotes within 4 weeks of award. Maintain 5% contingency reserve. | [Contracts Mgr] | [Date] | 2 | 3 | 6 | MEDIUM | Open - Monitoring | [Date] | Review quarterly against BCIS / Stats NZ index
R005 | HSE | Working at height incident — fall from leading edge or through opening | Inadequate edge protection; failure to use fall arrest; non-compliance with PTW | Fatality or serious injury; work stoppage; regulatory investigation; reputational damage | 6.3.1 | [EHS Manager] | 2 | 5 | 10 | HIGH | Mitigate | 100% edge protection installed before slab strike. Daily PTW for all >2m work. Weekly EHS inspections. Stop Work Authority briefed to all workers. | [EHS Officer] | [Date] | 1 | 5 | 5 | LOW | Open - Active | [Date] | ISO 45001 — critical risk. Never accept. Zero tolerance.
R006 | Schedule | Concrete supply disruption — ready-mix plant breakdown or driver shortage | Plant equipment failure; industrial action; supply chain capacity shortage | Pour programme halted; cold joints risk; 1–3 week delay to floor cycle | 2.2.1 | [Site Manager] | 3 | 4 | 12 | HIGH | Mitigate | Identify backup concrete supplier. Maintain pre-agreed alternative supply agreement. Test alternative supplier concrete mix design in advance. | [Site Manager] | [Date] | 2 | 2 | 4 | LOW | Open - Active | [Date] | Backup supplier to be pre-qualified before pours commence
R007 | Quality | Concrete non-conformance — cube test failure or honeycombing | Incorrect mix design; poor compaction; inadequate curing; contamination | Structural remediation required; programme delay 2–4 weeks; engineer investigation | 2.2.1 | [QA/QC Manager] | 2 | 4 | 8 | MEDIUM | Mitigate | Mandatory ITP hold points before each pour. Cube testing per BS EN 12390. Visual inspection 24hrs post-pour. NCR process in place. | [QA/QC Manager] | [Date] | 1 | 4 | 4 | LOW | Open - Active | [Date] | Structural engineer approval required before remediation
R008 | Regulatory | Building consent / planning approval delayed or conditions imposed | Insufficient information in application; authority backlog; third-party objections | Site possession delayed 4–12 weeks; programme start delayed; holding costs | 1.1.3 | [PM] | 2 | 4 | 8 | MEDIUM | Mitigate | Engage authority pre-application. Submit complete application. Appoint consent specialist. Track application weekly. | [PM] | [Date] | 1 | 3 | 3 | LOW | Open - Monitoring | [Date]
R009 | Commercial | Subcontractor insolvency — critical package subcontractor enters liquidation | Financial distress of subcontractor; over-commitment on multiple projects; payment disputes | Programme delay 6–10 weeks; step-in costs; bond claim; remobilisation cost | 2.0 | [Contracts Mgr] | 2 | 5 | 10 | HIGH | Transfer | Performance bond required on all packages >$500k. Quarterly financial health check on critical subs. Step-in clause in all subcontracts. | [Contracts Mgr] | [Date] | 1 | 4 | 4 | LOW | Open - Monitoring | [Date] | Bond claim process to be rehearsed before award
R010 | Environmental | Discovery of contaminated soil or hazardous materials during excavation | Site history not fully investigated; historical industrial use; undocumented fill | Work stoppage; regulatory notification; remediation cost $50k–$500k+; programme delay | 2.1.1 | [EHS Manager] | 2 | 4 | 8 | MEDIUM | Mitigate | Phase 1 & 2 ESA completed pre-construction. Contamination contingency in budget. Unexpected finds protocol in place. Regulatory contact identified. | [EHS Manager] | [Date] | 1 | 3 | 3 | LOW | Open - Monitoring | [Date]
R011 | Design | Scope of works ambiguity — interface between Main Contractor and subcontractors | Incomplete scope matrix; undefined trade interfaces; design not coordinated at boundaries | Variation disputes; abortive work; programme delay; relationship deterioration | 1.3.1 | [Contracts Mgr] | 3 | 3 | 9 | MEDIUM | Mitigate | Complete Subcontract Scope Matrix before award. Interface meetings monthly. Formal scope clarification process for all disputes. | [PM] | [Date] | 2 | 2 | 4 | LOW | Open - Active | [Date] | Scope matrix to be signed by all parties at award
R012 | Schedule | BIM / MEP coordination clash resolution delay | Under-resourced coordination; multiple consultants; late design information | MEP installation delayed; rework on site; programme delay 2–4 weeks | 1.2.3 | [MEP Engineer] | 3 | 3 | 9 | MEDIUM | Mitigate | Weekly clash resolution meetings with named owners. Target <20 open clashes before installation commences. BIM coordinator has sign-off authority. | [BIM Manager] | [Date] | 2 | 2 | 4 | LOW | Open - Active | [Date]
R013 | Force Majeure | Extreme weather event causing site flooding or wind stoppage | Seasonal storms; climate events; unforeseen rainfall intensity | Site closure 3–10 days; plant damage; programme delay; possible EOT claim | 6.0 | [Site Manager] | 2 | 3 | 6 | MEDIUM | Accept | Weather monitoring via Bureau of Meteorology / MetService. Contingency days in programme. Site drainage plan in place. FIDIC Clause 8.4(d) EOT entitlement. | [Site Manager] | [Date] | 2 | 3 | 6 | MEDIUM | Open - Monitoring | [Date] | EOT only — no cost compensation under standard FIDIC
R014 | Stakeholder | Community / neighbour complaint causing work restriction notice | Noise, dust, vibration from construction; inadequate community engagement | Restricted working hours; programme impact; reputational damage; council intervention | 6.0 | [PM] | 2 | 3 | 6 | MEDIUM | Mitigate | Community engagement plan activated at mobilisation. Noise / vibration monitoring. Neighbour notification before major pours. Complaints register maintained. | [PM] | [Date] | 1 | 2 | 2 | LOW | Open - Monitoring | [Date]
R015 | Cost | Variation / change order volume exceeds 10% of contract value | Incomplete design at tender; scope creep; excessive client-initiated changes | Contract value increase; programme delay; margin reduction; potential dispute | 6.0 | [QS / Controls] | 3 | 4 | 12 | HIGH | Mitigate | Strict change control process from day 1. Formal VO register. Change board review weekly. Client notified of cumulative impact at each 2% milestone. | [Contracts Mgr] | [Date] | 2 | 3 | 6 | MEDIUM | Open - Active | [Date]
R016 | Procurement | Nominated subcontractor performance failure — delays or poor quality | Inadequate pre-qualification; under-resourced; unfamiliar with local conditions | Programme delay; quality defects; potential re-work; main contractor liability | 1.3.1 | [PM] | 2 | 4 | 8 | MEDIUM | Mitigate | ITP in place for all nominated subs. Weekly performance KPI review. Step-in rights clearly defined. Back-charge mechanism in subcontract. | [Site Manager] | [Date] | 1 | 3 | 3 | LOW | Open - Active | [Date]
R017 | HSE | Crane accident — collision, dropped load, or overturning | Inadequate lift plan; mechanical failure; operator error; ground condition failure | Fatality or serious injury; major plant loss; project shutdown; regulatory investigation | 6.3.1 | [EHS Manager] | 1 | 5 | 5 | LOW | Mitigate | Appointed Lifting Supervisor for all lifts. Crane Load Charts verified. Ground bearing capacity checked. Lift plans for all critical lifts. No work under suspended loads. | [EHS Manager] | [Date] | 1 | 5 | 5 | LOW | Open - Active | [Date] | Critical risk — never accept
R018 | Quality | Waterproofing membrane failure — water ingress to basement or wet areas | Poor workmanship; damaged membrane; inadequate inspection; premature traffic | Water ingress; structural damage; remediation cost; occupier claims | 2.1.4 | [QA/QC Manager] | 2 | 4 | 8 | MEDIUM | Mitigate | ITP hold points before and after membrane installation. Flood test before covering. Independent QA inspector sign-off. Warranty certificates obtained. | [QA/QC Manager] | [Date] | 1 | 3 | 3 | LOW | Open - Monitoring | [Date]
R019 | Commercial | FIDIC Extension of Time (EOT) dispute with Employer | Delayed drawings; employer-risk events; concurrent delay; inadequate records | Programme extension not recognised; LDs applied; prolongation cost dispute | 6.0 | [Contracts Mgr] | 2 | 4 | 8 | MEDIUM | Mitigate | Contemporaneous daily records. Formal FIDIC notices within 28 days. Programme updates monthly. Delay analyst engaged if SPI <0.90. | [Contracts Mgr] | [Date] | 1 | 3 | 3 | LOW | Open - Monitoring | [Date] | FIDIC Sub-Clause 20.1 — 28-day notice critical
R020 | Schedule | Labour shortage — key trade workers unavailable in local market | Competing projects in market; seasonal demand; immigration restrictions; skills gap | Programme delay 2–6 weeks; productivity loss; overtime premium cost increase | 6.2.1 | [Site Manager] | 2 | 3 | 6 | MEDIUM | Mitigate | Resource plan agreed 8 weeks in advance. Back-to-back with subcontracts. Consideration of FIFO workforce. Weekly headcount vs plan check. | [Site Manager] | [Date] | 1 | 3 | 3 | LOW | Open - Monitoring | [Date]
TOTAL RISKS: 20 ¦ Input Prob & Impact (1–5) in blue cols — Score auto-calculates | [6 empty] | CRITICAL: =COUNTIF(K9:K28,"CRITICAL") | VERY HIGH: =COUNTIF(K9:K28,"VERY HIGH") | HIGH: =COUNTIF(K9:K28,"HIGH") | MEDIUM: =COUNTIF(K9:K28,"MEDIUM") | LOW: =COUNTIF(K9:K28,"LOW")
▲ Triangle PM · © 2026 · Risk Register · ISO 31000:2018 / PMBOK 7th Ed. · CONFIDENTIAL — PMO Use Only

## RISK SUMMARY
▲ TRIANGLE PM ¦ RISK SUMMARY DASHBOARD
Auto-calculated from Risk Register · ISO 31000:2018 · Review weekly in project meeting
KPI | Pre-Mitigation | Post-Mitigation | Trend | Target | Status
Total Risks | 20 | 20 | → | < 30 active | —
CRITICAL Risks | 0 | 0 | ↓ Target | 0 | —
VERY HIGH Risks | 2 | 0 | ↓ Target | ≤ 2 | —
HIGH Risks | 6 | 0 | ↓ Target | ≤ 5 | —
MEDIUM Risks | 11 | 6 | → | ≤ 10 | —
LOW Risks | 1 | 14 | ↑ Good | Majority | —
Open - Active | 11 | — | → | Track weekly | —
Mitigated / Closed | 0 | — | ↑ Good | Ongoing | —
▲ Triangle PM · © 2026 · Risk Summary · CONFIDENTIAL

## INSTRUCTIONS
▲ TRIANGLE PM ¦ RISK REGISTER — USER GUIDE
ISO 31000:2018 · PMBOK 7th Ed. · Construction Risk Management
PROBABILITY & IMPACT SCALE (1–5)
• 1 — Rare / Negligible: Very unlikely to occur (<10%). Cost impact < 0.5% of budget. <1 week delay.
• 2 — Unlikely / Minor: Unlikely but possible (10–30%). Cost impact 0.5–2%. 1–2 week delay.
• 3 — Possible / Moderate: Even chance (30–50%). Cost impact 2–5%. 2–4 week delay.
• 4 — Likely / Major: More likely than not (50–70%). Cost impact 5–10%. 1–2 month delay.
• 5 — Almost Certain / Catastrophic: Very likely (>70%). Cost impact >10%. >2 month delay.
RISK SCORE & RATING THRESHOLDS
• Score 1–5 (P×I) → LOW — Monitor monthly. Include in risk register. No immediate action.
• Score 6–9 (P×I) → MEDIUM — Monitor weekly. Assign owner. Review mitigation actions.
• Score 10–14 (P×I) → HIGH — Active mitigation required. Report to PM weekly. Recovery plan if triggered.
• Score 15–19 (P×I) → VERY HIGH — Escalate to senior PM immediately. Dedicated mitigation owner. Weekly update.
• Score 20–25 (P×I) → CRITICAL — Immediate escalation to Executive. Stop work if safety-related. Daily tracking.
RESPONSE STRATEGIES (ISO 31000)
• Avoid — Eliminate the risk entirely by changing approach, scope, or design.
• Transfer — Shift the financial consequence to another party (insurance, warranty, subcontract clause).
• Mitigate — Reduce probability and/or impact through specific control actions.
• Accept — Acknowledge the risk and establish a contingency budget and/or programme float.
• Exploit (Opportunities only) — Increase probability of a positive risk occurring.
• Share (Opportunities only) — Share the benefit of a positive risk with another party.
HOW TO USE THIS REGISTER
• Step 1 — Enter project details in the RISK REGISTER header strip (Project Name, No., Client, Date).
• Step 2 — For each risk, enter Probability (H col) and Impact (I col) as a number 1–5. Score auto-calculates.
• Step 3 — Select Category and Response Strategy from the dropdown lists.
• Step 4 — Write a specific, actionable mitigation in Column M with a named owner and due date.
• Step 5 — After mitigation is in place, enter Residual Probability (P col) and Impact (Q col). Residual score auto-calculates.
• Step 6 — Review the Top 10 risks in the project meeting every week. Update status, owner, and last-reviewed date.
• Step 7 — Close risks when the trigger date has passed or mitigation is complete. Archive — never delete.
• Step 8 — Transfer HIGH and CRITICAL residual risks to the RISK HEAT MAP for visual reporting to stakeholders.
ISO 31000 & PMBOK BEST PRACTICES
• Every risk must have ONE named owner — a person, not a role or discipline. Shared ownership = no ownership.
• Mitigation actions must be SPECIFIC: 'Obtain backup supplier pre-qualification by [Date]' not 'Manage supply risk'.
• Trigger conditions define WHEN to activate contingency. Write them at the time of risk identification.
• Residual score is the rating AFTER mitigation is in place — not the target. Be realistic, not optimistic.
• A risk register that never changes is not being used. Add, close, and update risks weekly without exception.
• Link the risk register to the contingency reserve: each HIGH/CRITICAL risk should have a cost-at-risk figure.
• Transfer HIGH/CRITICAL risks to the RISK HEAT MAP sheet for every monthly owner/client report.
▲ Triangle PM · © 2026 · Risk Register · ISO 31000:2018 · CONFIDENTIAL