## WBS REGISTER
▲ TRIANGLE PM ¦ WBS MASTER TEMPLATE | [9 empty] | PROJECT CONTROLS
Work Breakdown Structure · PMBOK 7th Ed. / ISO 21502 · 4-Level Hierarchy · WBS Dictionary Integrated
PROJECT: |  | [Project Name] |  |  |  | PROJECT NO: |  |  | [Project No.] |  | CONTRACT VALUE: |  | [Enter Value — USD]
CLIENT: |  | [Client Name] |  |  |  | BASELINE DATE: |  |  | [DD-Mon-YYYY] |  | WBS VERSION: |  | Rev 1 — [Date]
WBS Code | Level 1 Phase | Level 2 Category | Level 3 Sub-Category | Level 4 — Work Package / Deliverable | Key Deliverable / Output | Responsible Party | Cost Account Code | Original Budget ($) | Actual Cost ($) | ETC ($) | % Plan Complete | Status | Planned Start | Planned Finish | Remarks / Notes
1 · 1. PRECONSTRUCTION
1.1 · 1.1 Project Initiation
1.1.1 · 1.1.1 Project Charter
1.1.2 · 1.1.2 Mobilisation Plan
1.1.3 · 1.1.3 PMO Setup & Procedures
1.2 · 1.2 Design Management
1.2.1 · 1.2.1 Concept & Developed Design
1.2.2 · 1.2.2 IFC Drawing Coordination
1.2.3 · 1.2.3 BIM Coordination
1.3 · 1.3 Procurement
1.3.1 · 1.3.1 Subcontract Packages
1.3.2 · 1.3.2 Long-Lead Procurement
2 · 2. CIVIL & STRUCTURAL
2.1 · 2.1 Substructure
2.1.1 · 2.1.1 Site Clearance & Prep
2.1.2 · 2.1.2 Piling Works
2.1.3 · 2.1.3 Pile Caps & Ground Beams
2.1.4 · 2.1.4 Basement Retaining Walls
2.1.5 · 2.1.5 Basement Slabs
2.2 · 2.2 Superstructure
2.2.1 · 2.2.1 Core Walls — All Levels
2.2.2 · 2.2.2 Suspended Slabs — All Levels
2.2.3 · 2.2.3 Structural Steelwork
3 · 3. MEP SERVICES
3.1 · 3.1 Mechanical
3.1.1 · 3.1.1 HVAC Systems
3.1.2 · 3.1.2 Plumbing & Drainage
3.1.3 · 3.1.3 Fire Suppression
3.2 · 3.2 Electrical
3.2.1 · 3.2.1 MV Switchgear & Transformers
3.2.2 · 3.2.2 LV Distribution & Wiring
3.2.3 · 3.2.3 Lighting & Controls
3.3 · 3.3 Vertical Transport
3.3.1 · 3.3.1 Passenger Lifts
4 · 4. ARCHITECTURAL & FINISHES
4.1 · 4.1 Façade & Cladding
4.1.1 · 4.1.1 Curtain Wall System
4.1.2 · 4.1.2 External Render & Insulation
4.2 · 4.2 Internal Finishes
4.2.1 · 4.2.1 Internal Blockwork Partitions
4.2.2 · 4.2.2 Drylining & Plasterboard
4.2.3 · 4.2.3 Floor Screeds & Tiling
4.2.4 · 4.2.4 Painting & Decoration
4.3 · 4.3 FF&E
4.3.1 · 4.3.1 Furniture, Fixtures & Equipment
5 · 5. EXTERNAL WORKS
5.1 · 5.1 Landscaping & Hardscaping
5.1.1 · 5.1.1 Landscape & Planting
5.1.2 · 5.1.2 External Paving & Roads
5.2 · 5.2 External Services
5.2.1 · 5.2.1 External Drainage & Utilities
6 · 6. PROJECT MANAGEMENT (PRELIMS)
6.1 · 6.1 PMO & Controls
6.1.1 · 6.1.1 Programme Management
6.1.2 · 6.1.2 Cost Management
6.1.3 · 6.1.3 Risk Management
6.1.4 · 6.1.4 Quality Management
6.2 · 6.2 Site Establishment
6.2.1 · 6.2.1 Temporary Works & Fencing
6.2.2 · 6.2.2 Site Accommodation & Offices
6.3 · 6.3 Health, Safety & Environment
6.3.1 · 6.3.1 EHS Management System
6.3.2 · 6.3.2 Environmental Management
TOTAL PROJECT BUDGET (WBS ROLL-UP) | [7 empty] | 0 | 0 | 0
▲ Triangle PM · © 2026 · WBS Master Template · PMBOK 7th Ed. / ISO 21502 · CONFIDENTIAL

## WBS DICTIONARY
▲ TRIANGLE PM ¦ WBS DICTIONARY
Each Work Package defined with scope boundary, acceptance criteria, responsible party & dependencies · PMBOK 7th Ed.
WBS Code | Work Package Name | Scope Boundary (What IS Included) | Acceptance Criteria / Deliverable | Responsible Party | Required Resources | Dependencies (Predecessors) | Notes / Assumptions
1.1.1 | Project Charter | Develop the project charter covering project purpose, objectives, scope summary, authority matrix, key stakeholders, and success criteria. Obtain signatures from all required parties. | Signed Project Charter approved by [Client Representative] and [Contractor PM]. Filed in project management information system. Version controlled. | [Project Manager / PMO] | Project Manager, Senior PM, Client Representative | None | Prerequisite for all subsequent work packages
1.2.2 | IFC Drawing Coordination | Manage and coordinate production, review, comment, and approval of all Issued-for-Construction (IFC) drawings across all disciplines. Maintain the IFC Drawing Register. | 100% IFC Drawing Register with Client / Engineer approval stamps. No design queries blocking construction in any active zone. | [Lead Engineer] | Design team, Sub-consultants, BIM Manager | 1.2.1 | BIM coordination to run concurrently
2.1.2 | Piling Works | Supply, install, and test all bored cast-in-situ reinforced concrete piles to structural engineer's specification. Includes pile load testing, integrity testing, and as-built survey. | Pile integrity test reports (PIT) — all piles pass. Pile load test (SLT/MLT) results approved by Structural Engineer. As-built pile survey approved. | [Piling Sub] | Piling rig, casing, concrete, rebar, testing lab | 1.1.2, 2.1.1 | FIDIC Clause 7 testing and inspection
2.2.1 | Core Walls — All Levels | Formwork, reinforce, pour and cure all RC core walls from Level 1 to top level per structural drawings. Includes MEP box-outs per coordinated drawings. | Concrete cube test results passing at 28 days. Structural inspection record signed by Engineer each level. Dimensional survey within tolerance. | [Concrete Sub] | Jump-form system, rebar, crane, pump, testing lab | 2.1.5 | CRITICAL PATH — monitor weekly
3.1.1 | HVAC Systems | Design, supply, install, test, balance, and commission all HVAC systems including chillers, AHUs, FCUs, ductwork, controls, and BMS integration per MEP specification. | Commissioning report approved by MEP Engineer. BMS integration tested and operational. TAB (Test, Adjust, Balance) report complete. O&M manuals submitted. | [Mechanical Sub] | MEP contractor, test equipment, commissioning engineer | Structural complete in zone | Coordination with electrical essential
3.2.2 | LV Distribution & Wiring | Supply and install all LV distribution boards, sub-main cables, final circuit wiring, containment systems, and terminations per electrical specification. | Cable test reports (insulation resistance, continuity). Board schedules certified by Electrical Engineer. Authority approval obtained. | [Electrical Sub] | Cables, cable trays, boards, test equipment | 3.2.1 | First fix concurrent with structure — plan early
4.1.1 | Curtain Wall System | Design, fabricate, supply, install, test and commission unitised curtain wall system to architectural specification. Includes mock-up approval, air and water-tightness testing. | Mock-up approved by Client and Architect. Water penetration test passed. Air infiltration test passed. Thermal performance calculations approved. | [Façade Sub] | CW units, framing, sealant, crane, test equipment | Structure complete in zone | Mock-up inspection — all parties required
6.1.1 | Programme Management | Prepare, baseline, maintain, and update the master project programme. Produce weekly 3-week look-ahead schedules, monthly programme narrative, and all schedule reporting. | Baseline programme approved by Client. Weekly look-ahead issued every Monday. Monthly programme narrative with SPI / variance analysis. | [PM / Project Planner] | P6 / MS Project licence, planner resource | None | Last Planner System® PPC tracked weekly
6.3.1 | EHS Management System | Implement and maintain the project EHS Management System compliant with ISO 45001:2018. Includes site safety plan, toolbox talks, incident reporting, inspections, and reporting. | Zero LTI sustained throughout construction. Weekly EHS inspection reports. Toolbox talk records for all operatives. Monthly EHS report to Client. | [EHS Manager] | EHS officer resource, PPE, inspection forms | None | LTI rate monitored and reported monthly
▲ Triangle PM · © 2026 · WBS Dictionary · CONFIDENTIAL

## WBS SUMMARY
▲ TRIANGLE PM ¦ WBS BUDGET SUMMARY
Cost roll-up by Level 1 Phase · Auto-populated from WBS Register
WBS Phase | Budget ($) | Actual Cost ($) | ETC ($) | % Expended
1. Preconstruction | 0 | 0 | 0
2. Civil & Structural | 0 | 0 | 0
3. MEP Services | 0 | 0 | 0
4. Architectural & Finishes | 0 | 0 | 0
5. External Works | 0 | 0 | 0
6. Project Management | 0 | 0 | 0
TOTAL PROJECT | 0 | 0 | 0
▲ Triangle PM · © 2026 · WBS Summary · CONFIDENTIAL